## Sheet1
Period | From | To | Plan | Comments | Done
Week 6 | 2014-04-07 | 2014-04-13 | Get familiar with Parallel Iterator
Break | 2014-04-14 | 2014-04-20 | Get familiar with Parallel Iterator Research situations with partial ordering and devise a way to communicate that to PI
Break | 2014-04-21 | 2014-04-27 | Research situations with partial ordering and devise a way to communicate that to PI Prepare seminar
Week 7 | 2014-04-28 | 2014-05-04 | Seminar Tuesday 29th April 2:30pm
Week 8 | 2014-05-05 | 2014-05-11 | Drafting report, implementation, testing
Week 9 | 2014-05-12 | 2014-05-18 | Drafting report, implementation, testing | Busy
Week 10 | 2014-05-19 | 2014-05-25 | Drafting report, implementation, testing | Busy
Week 11 | 2014-05-26 | 2014-06-01 | Report finishing, implementation, testing | Busy
Week 12 | 2014-06-02 | 2014-06-08 | Report and implementation due | Busy